## Project Planner
Product Inventory Management System
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Plan Duration | [5 empty] | Start |  |  |  |  | % Complete
ACTIVITY | DURATION | START | END | PERIODS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89
Requirements Gathering | 2 WEEKS | 2024-08-12 | 2024-08-25 | bar: PERIODS 1 to PERIODS 14
Conduct surveys/interviews with business owners. |  | 2024-08-12 | 2024-08-14 | bar: PERIODS 1 to PERIODS 3
Define system requirements based on user needs. |  | 2024-08-15 | 2024-08-19 | bar: PERIODS 4 to PERIODS 8
Proposal Presentation |  | 2024-08-20 | 2024-08-25 | bar: PERIODS 9 to PERIODS 14
System Design | 2 WEEKS | 2024-08-26 | 2024-09-08 | bar: PERIODS 15 to PERIODS 28
Design User Interface |  | 2024-08-26 | 2024-09-05 | bar: PERIODS 15 to PERIODS 25
Database Design |  | 2024-08-26 | 2024-09-05 | bar: PERIODS 15 to PERIODS 25
System Architecture |  | 2024-08-26 | 2024-09-05 | bar: PERIODS 15 to PERIODS 25
Finalize Design Document |  | 2024-09-06 | 2024-09-08 | bar: PERIODS 26 to PERIODS 28
Development | 4 WEEKS | 2024-09-09 | 2024-10-07 | bar: PERIODS 29 to PERIODS 56
Set Up Development Environment |  | 2024-09-16 | 2024-10-07 | bar: PERIODS 36 to PERIODS 56
Front-End Development |  | 2024-09-16 | 2024-10-07 | bar: PERIODS 36 to PERIODS 56
Back-End Development |  | 2024-09-16 | 2024-10-07 | bar: PERIODS 36 to PERIODS 56
Integrate UI with Back-End |  | 2024-09-16 | 2024-10-07 | bar: PERIODS 36 to PERIODS 56
Data Export Feature |  | 2024-09-16 | 2024-10-07 | bar: PERIODS 36 to PERIODS 56
Testing | 9 WEEKS | 2024-08-26 | 2024-10-27 | bar: PERIODS 15 to PERIODS 89
Demonstration | bar: PERIODS 57 to PERIODS 58
Demonstration 1 |  | 2024-09-09 | 2024-09-15 | bar: PERIODS 29 to PERIODS 35; PERIODS 57 to PERIODS 58
Demonstration 2 |  | 2024-10-08 | 2024-10-13 | bar: PERIODS 57 to PERIODS 58
Demonstration 3 |  | 2024-11-04 | 2024-11-10 | bar: PERIODS 83 to PERIODS 89
Deployment | 1 WEEKS | 2024-10-21 | 2024-10-27 | bar: PERIODS 67 to PERIODS 73
Set Up Hosting Environment |  | 2024-10-21 | 2024-10-24 | bar: PERIODS 67 to PERIODS 70
Final System Testing |  | 2024-10-25 | 2024-10-26 | bar: PERIODS 71 to PERIODS 72
Launch the system |  | 2024-10-27 | 2024-10-27 | bar: PERIODS 73
Maintenance | Ongoing | 2024-11-04 | Ongoing | bar: PERIODS 83 to PERIODS 89